## Budget
Most Devoted
Sprint Budget |  |  |  |  | Time Remaining
| December | January | February |  |  | December | January | February
Connect to Database | 3 | 0.5 | 0.5 | 4 | Connect to Database | 2 | 0.5 | 0.5 | 3
UI to Edit Database | 1 | 5 | 4 | 10 | UI to Edit Database | 1 | 5 | 4 | 10
CSV Parsing | 0 | 2 | 3 | 5 | CSV Parsing | 0 | 2 | 3 | 5
Export Database | 0 | 0.5 | 1 | 1.5 | Export Database | 0 | 0.5 | 1 | 1.5
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
Testing & Debugging | 0.5 | 4 | 3.5 | 8 | Testing & Debugging | 0 | 4 | 3.5 | 7.5
Research and Dev't | 3 | 4 | 4 | 11 | Research and Dev't | 2 | 4 | 4 | 10
Documentation | 6 | 4 | 3 | 13 | Documentation | 1.5 | 4 | 3 | 8.5
Others |  |  |  | 0 | Others | 0 | 0 | 0 | 0
| 13.5 | 20 | 19 | 52.5 |  | 6.5 | 20 | 19 | 45.5

## Actual
| DECEMBER | [14 empty] | JANUARY | [30 empty] | FEBRUARY
 | time axis 2012-12-17 to 2013-02-17
Connect to Database | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UI to Edit Database | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSV Parsing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Export Database | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing & Debugging | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Research and Dev't | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weekly | 2012-12-20: 7; 2012-12-27: 0; 2013-01-03: 0; 2013-01-10: 0; 2013-01-17: 0; 2013-01-24: 0; 2013-01-31: 0; 2013-02-07: 0; 2013-02-14: 0
Most Devoted | 2012-12-17: Matthew
Monthly | 2012-12-17: 7; 2013-01-01: 0; 2013-02-01: 0
Most Devoted

## Matthew
| DECEMBER | [14 empty] | JANUARY | [30 empty] | FEBRUARY
 | time axis 2012-12-17 to 2013-02-17
Connect to Database | bar: 2012-12-17
UI to Edit Database
CSV Parsing
Export Database
Testing & Debugging | 2012-12-17: 0.5
Research and Dev't | bar: 2012-12-17
Documentation | 2012-12-17: 4.5
Others
Daily | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weekly | 2012-12-20: 7; 2012-12-27: 0; 2013-01-03: 0; 2013-01-10: 0; 2013-01-17: 0; 2013-01-24: 0; 2013-01-31: 0; 2013-02-07: 0; 2013-02-14: 0
Monthly | 2012-12-17: 7; 2013-01-01: 0; 2013-02-01: 0

## Fatima
| DECEMBER | [14 empty] | JANUARY | [30 empty] | FEBRUARY
 | time axis 2012-12-17 to 2013-02-17
Connect to Database
UI to Edit Database
CSV Parsing
Export Database
Testing & Debugging
Research and Dev't
Documentation
Others
Daily | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weekly | 2012-12-20: 0; 2012-12-27: 0; 2013-01-03: 0; 2013-01-10: 0; 2013-01-17: 0; 2013-01-24: 0; 2013-01-31: 0; 2013-02-07: 0; 2013-02-14: 0
Monthly | 2012-12-17: 0; 2013-01-01: 0; 2013-02-01: 0

## Molen
| DECEMBER | [14 empty] | JANUARY | [30 empty] | FEBRUARY
 | time axis 2012-12-17 to 2013-02-17
Connect to Database
UI to Edit Database
CSV Parsing
Export Database
Testing & Debugging
Research and Dev't
Documentation
Others
Daily | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weekly | 2012-12-20: 0; 2012-12-27: 0; 2013-01-03: 0; 2013-01-10: 0; 2013-01-17: 0; 2013-01-24: 0; 2013-01-31: 0; 2013-02-07: 0; 2013-02-14: 0
Monthly | 2012-12-17: 0; 2013-01-01: 0; 2013-02-01: 0

## Jayme
| DECEMBER | [14 empty] | JANUARY | [30 empty] | FEBRUARY
 | time axis 2012-12-17 to 2013-02-17
Connect to Database
UI to Edit Database
CSV Parsing
Export Database
Testing & Debugging
Research and Dev't
Documentation
Others
Daily | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weekly | 2012-12-20: 0; 2012-12-27: 0; 2013-01-03: 0; 2013-01-10: 0; 2013-01-17: 0; 2013-01-24: 0; 2013-01-31: 0; 2013-02-07: 0; 2013-02-14: 0
Monthly | 2012-12-17: 0; 2013-01-01: 0; 2013-02-01: 0

## Janeri
| DECEMBER | [14 empty] | JANUARY | [30 empty] | FEBRUARY
 | time axis 2012-12-17 to 2013-02-17
Connect to Database
UI to Edit Database
CSV Parsing
Export Database
Testing & Debugging
Research and Dev't
Documentation
Others
Daily | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weekly | 2012-12-20: 0; 2012-12-27: 0; 2013-01-03: 0; 2013-01-10: 0; 2013-01-17: 0; 2013-01-24: 0; 2013-01-31: 0; 2013-02-07: 0; 2013-02-14: 0
Monthly | 2012-12-17: 0; 2013-01-01: 0; 2013-02-01: 0

## Telle
| DECEMBER | [14 empty] | JANUARY | [30 empty] | FEBRUARY
 | time axis 2012-12-17 to 2013-02-17
Connect to Database
UI to Edit Database
CSV Parsing
Export Database
Testing & Debugging
Research and Dev't
Documentation
Others
Daily | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weekly | 2012-12-20: 0; 2012-12-27: 0; 2013-01-03: 0; 2013-01-10: 0; 2013-01-17: 0; 2013-01-24: 0; 2013-01-31: 0; 2013-02-07: 0; 2013-02-14: 0
Monthly | 2012-12-17: 0; 2013-01-01: 0; 2013-02-01: 0

## Data (hidden)
7 | Matthew | 0 | Matthew | 0 | Matthew | 0 | Matthew | 0 | Matthew | 0 | Matthew | 0 | Matthew
0 | Fatima | 0 | Fatima | 0 | Fatima | 0 | Fatima | 0 | Fatima | 0 | Fatima | 0 | Fatima
0 | Molen | 0 | Molen | 0 | Molen | 0 | Molen | 0 | Molen | 0 | Molen | 0 | Molen
0 | Jayme | 0 | Jayme | 0 | Jayme | 0 | Jayme | 0 | Jayme | 0 | Jayme | 0 | Jayme
0 | Janeri | 0 | Janeri | 0 | Janeri | 0 | Janeri | 0 | Janeri | 0 | Janeri | 0 | Janeri
0 | Telle | 0 | Telle | 0 | Telle | 0 | Telle | 0 | Telle | 0 | Telle | 0 | Telle
7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0